## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story? | Velocity
1 | As a not logged in/ logged in User of the AWG Hub, I can go from the Hub Page to any of its subdomains (Clubs) for viewing/surffing them. | 2 | Sherry |  |  | 0.02
2 | As a not logged in/ logged in User of the AWG Hub, I can see on the AWG Hub's homepage the provided brief description of the clubs. | 2 | Sherry |  |  | 0.033
3 | As a not logged in/ logged in User of the AWG Hub, I can view the public announcements made by AWGs' subdomains on the hub. | 2 | Amr |  |  | 0.011
4 | As a Logged in user (visitor) and not a member of the club, I should be able to click and fill in the application form. | 3 | Maha |  |  | 0.05
4.1 | As an “Applicant” I should be able to view (keep track of) my application to review the status. | 3 | Maha |  |  | 0.05
4.2 | As a “President/Director”, I can view the application forms for accepting, binding, or rejecting the applicant. | 3 | Maha |  |  | 0.05
4.3 | As a Head, I can view the application form of my committee for accepting, binding, or rejecting the applicant. | 3 | Maha |  |  | 0.05
4.4 | As a HR Head/Director/President, I should be able to edit the fields in the recruitment forms. | 3 | Maha |  |  | 0.01
5 | As a not logged in/logged in user of the AWG Hub, I can view all the Events pages and see the descritption of the events. | 2 | Merna |  |  | 0.0083
5.1 | As a logged in visitor, I should be able to fill public event forms to submit the fact that I am attending. | 2 | Merna |  |  | 0.0083
5.2 | As a “Member/Heads/Directors/President” I should be able to fill out private club event forms to be able to attend them. | 2 | Merna |  |  | 0.0083
5.3 | As a logged/not logged in user (outsider (Not a gucian)), I can attend public events by providing National ID number in the form | 3 | Merna |  |  | 0.0083
6 | As a Head/Director/President, I can view event submission forms to filter through them. | 2 | Osama
7 | As a Marketing Head/Directors/President, I can add/edit/remove events. | 2 | Osama
8 | As a Heads/Directors/President, I should be able to add notes to the users under me (or in the same committee for Heads) to be reviewed later on | 2 | Sara |  |  | 0.016
9 | As a HR Head/Director/President, I can edit the amount, the start and end of the interview slots. | 2 | Amr |  |  | 0.011
10 | As a HR Head, I can assign the booth members. | 2 | Ghada |  |  | 0.044
10.1 | As a “booth member” I should be able to book/change interview times in respect to the free slots in the interview sheets of the heads. | 3 | Ghada |  |  | 0.033
10.2 | As a Head, I should be able to create/ view/ edit my own interview slot sheet which is a table that indicates my free slots. | 2 | Ghada |  |  | 0.0083
10.2 | As a Head, I should be able to create/ view/ edit my own interview slot sheet which is a table that indicates my free slots. | 2 | Ghada |  |  | 0.0083
11 | As a “Member/Head/Director/President” I should be able to view my attendance. | 2 | Omar |  |  | 0.016
11.1 | As a President I can view the attendances of all the club’s members/ heads/ directors. | 2 | Omar |  |  | 0.016
11.2 | As a Director I can view the attendance of the mentors or heads and members. | 2 | Omar |  |  | 0.016
11.3 | As a Head, I can view the attendance of the recruits or members in the same branch. | 2 | Omar |  |  | 0.016
12 | As a Heads/Directors/President, I should be able to edit the attendance sheets of the members. | 2 | Seif | Omar's User story | I should be able to view the attendance sheet then edit the attendance sheet | 0.033
12.1 | As a President, or Director, I can easily access a page that contains all the information of my present and past applicants. | 2 | Seif |  |  | 0.033
12.2 | As a Head of a certain committee, I can access a page that contains all the information related only to my committee's present and past applicants. | 2 | Seif |  |  | 0.033
13 | As a Signed in user in AWG Hub, I can view and edit all my information from my AWGs profile. | 2 | Passant |  |  | 0.011
13.1 | As a logged in/ not logged in user of the AWG Hub, I can view FAQs on the hub | 2 | Passant |  |  | 0.011
14 | As a logged in user in AWG Hub, I should have a VGS profile that contains all of my details. | 2 | Sara |  |  | 0.016
15 | As a Signed in user in AWG Hub, I can view and edit all my information from my AWGs profile. | 2 | Amina |  |  | 0.011
(per min)
[6 empty] | team velocity | 0.7035/26 | 1407/52000
|  |  | Total SP | 69
Actual
|  |  | Estimated | 69/7=9.8

## Sheet2
days | user stories
1 | 0
2 | 0
3 | 2
4 | 3
5 | 5
6 | 5
7 | 11