## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As a “President/Director/Head” I can post announcements whether to a committee or a specific user, and I can post with it whether a text, pdf, or picture. | 3 | Omar | Ghada | Seif
2 | As a President/Director/Head, I can create a group to send announcements to whom I choose and it's only controlled and accessible by me | 3 | Ghada | Merna | Maha
3 | As a Head, I should be able to add members or remove them from my committee. | 3 | Sherry | Maha | Sara
4 | As a Director/President, I should be able to edit accounts of users or remove users under me. | 3 | Sherry | Sara | Merna
5 | As a Heads, I can send a request to my Director asking for a permission to edit the user profiles under my committee to remove unapproved content. | 3 | Merna | Maha | Osama
6 | As a Director, I should be able to raise a vote to replace the president with one of the current advisors or directors if they fit, and (if all the other directors vote also for the same person) it’s a unanimous vote that all the advisors/directors agree on. | 3 | Maha | Sherry | Merna
7 | As a President, I should be able to raise a vote to replace myself, and If all the directors agree and they all accepted the same nominated person, I can be changed. | 3 | Maha | Ghada | Sherry
8 | As an Admin of the AWG Hub, I can add users | 3 | Amina | Amr | Passant
9 | As an Admin of the AWG Hub, I can edit users | 3 | Amr | Amina | Passant
10 | As an Admin of the AWG Hub, I can delete users | 3 | Passant | Amr | Amina
11 | As an Admin of the AWG Hub, I can edit the FAQs section. | 3 | Sara | Sherry | Omar
12 | As a logged in/not logged in user, I can contact with the club through a contact us page, that sends the content directly to the club’s email. | 3 | Osama | Seif | Omar
13 | As a logged in/not logged in user in AWG Hub, I can check out the about us page that contains all of the info about the VGS club. | 3 | Seif | Ghada | Osama