## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2 | Hours | Velocity
1 | As a “booth member” I should be able to book/change interview times in respect to the free slots in the interview sheets of the heads. | 3 | Ghada | Merna | Maha | 2 | 1.5
2 | As a Head, I should be able to create/ view/ edit my own interview slot sheet which is a table that indicates my free slots. | 3 | Ghada | Merna | Maha | 2 | 1.5
3 | As a Logged in user (visitor) and not a member of the club, I should be able to click and fill in the application form. | 2 | Maha | Sherry | Ghada | 4 | 0.5
4 | As an “Applicant” I should be able to view (keep track of) my application to review the status | 2 | Maha | Sherry | Ghada | 4 | 0.5
5 | As a “President/Director”, I can view the application forms for accepting, pending, or rejecting the applicant. | 2 | Maha | Sherry | Ghada | 4 | 0.5
6 | As a HR Head/Director/President, I should be able to edit the fields in the recruitment forms | 3 | Maha | Sherry | Ghada | 4 | 0.75
7 | As a President, I should be able to raise a vote to replace myself, and If all the directors agree and they all accepted the same nominated person, I can be changed. | 3 | Maha | Sherry | Ghada | 5 | 0.6
8 | As a Director, I should be able to raise a vote to replace the president with one of the current advisors or directors if they fit, and (if all the other directors vote also for the same person) it’s a unanimous vote that all the advisors/directors agree on. | 3 | Maha | Sherry | Ghada | 5 | 0.6
9 | As a not logged in/ logged in User of the AWG Hub, I can go from the Hub Page to any of its subdomains (Clubs) for viewing/surffing them. | 2 | Sherry | Maha | Sara | 5 | 0.4
10 | As a not logged in/ logged in User of the AWG Hub, I can see on the AWG Hub's homepage the provided brief description of the clubs. | 2 | Sherry | Maha | Sara | 5 | 0.4
11 | As a Director/President, I should be able to edit accounts of users or remove users under me | 3 | Sherry | Maha | Sara | 5 | 0.6
12 | As a Head, I should be able to add members or remove them from my committee. | 3 | Sherry | Maha | Sara | 5 | 0.6
13 | As a not logged in/logged in user of the AWG Hub, I can view all the Events pages and see the descritption of the events. | 2 | Merna | Ghada | Maha | 2 | 1
14 | As a logged in visitor, I should be able to fill public event forms to submit the fact that I am attending. | 2 | Merna | Ghada | Maha | 2 | 1
15 | As a “Member/Heads/Directors/President” I should be able to fill out private club event forms to be able to attend them. | 2 | Merna | Ghada | Maha | 3 | 0.66667
16 | As a logged/not logged in user (outsider (Not a gucian)), I can attend public events by providing National ID number in the form | 2 | Merna | Ghada | Maha | 4 | 0.5
17 | As a Heads, I can send a request to my Director asking for a permission to edit the user profiles under my committee to remove unapproved content. | 3 | Merna | Ghada | Maha | 5 | 0.6
18 | As a director I can edit status of a request to refuse or accept it. | 3 | Merna | Ghada | Maha | 2 | 1.5
19 | As a head I can view specific request to check for acceptance or rejection. | 3 | Merna | Ghada | Maha | 2 | 1.5
20 | As a director I can view a specific request to check its data. | 3 | Merna | Ghada | Maha | 2 | 1.5
21 | As a Heads/Directors/President, I should be able to add notes to the users under me (or in the same committee for Heads) to be reviewed later on | 2 | Sara | Sherry | Maha | 3 | 0.66667
22 | As a logged in user in AWG Hub, I should have a VGS profile that contains all of my details. | 2 | Sara | Sherry | Maha | 3 | 0.66667
23 | As a logged in/ not logged in user of the AWG Hub, I can view FAQs on the hub | 2 | Sara | Sherry | Maha | 3 | 0.66667
24 | As an Admin of the AWG Hub, I can edit the FAQs section. | 2 | Sara | Sherry | Maha | 3 | 0.66667
25 | As a not logged in/ logged in User of the AWG Hub, I can view the public announcements made by AWGs' subdomains on the hub. | 2 | Amr | Amina | Passant | 3 | 0.66667
26 | As a HR Head/Director/President, I can edit the amount, the start and end of the interview slots. | 3 | Amr | Amina | Passant | 3 | 1
27 | As an Admin of the AWG Hub, I can edit users | 2 | Amr | Amina | Passant | 3 | 0.66667
28 | As a Head/Director/President, I can view event submission forms to filter through them. | 2 | Osama | Seif | Omar | 3 | 0.66667
29 | As a Marketing Head/Directors/President, I can add/edit/remove events. | 2 | Osama | Seif | Omar | 3 | 0.66667
30 | As a logged in/not logged in user, I can contact with the club through a contact us page, that sends the content directly to the club’s email. | 3 | Osama | Seif | Omar | 3 | 1
31 | As a “Member/Head/Director/President” I should be able to view my attendance. | 2 | Omar | Seif | Osama | 3 | 0.66667
32 | As a President I can view the attendances of all the club’s members/ heads/ directors. | 2 | Omar | Seif | Osama | 3 | 0.66667
33 | As a Director I can view the attendance of the mentors or heads and members. | 2 | Omar | Seif | Osama | 3 | 0.66667
34 | As a Head, I can view the attendance of the recruits or members in the same branch. | 2 | Omar | Seif | Osama | 3 | 0.66667
35 | As a “President/Director/Head” I can post announcements whether to a committee or a specific user, and I can post with it whether a text, pdf, or picture. | 3 | Omar | Seif | Osama | 3 | 1
36 | As a Heads/Directors/President, I should be able to edit the attendance sheets of the members | 2 | Seif | Omar | Osama | 3 | 0.66667
37 | As a President, or Director, I can easily access a page that contains all the information of my present and past applicants. | 2 | Seif | Omar | Osama | 3 | 0.66667
38 | As a Head of a certain committee, I can access a page that contains all the information related only to my committee's present and past applicants. | 2 | Seif | Omar | Osama | 3 | 0.66667
39 | As a logged in/not logged in user in AWG Hub, I can check out the about us page that contains all of the info about the VGS club. | 2 | Seif | Omar | Osama | 3 | 0.66667
40 | As a Signed in user in AWG Hub, I can view and edit all my information from my AWGs profile | 2 | Amina | Amr | Passant | 5 | 0.4
41 | As an Admin of the AWG Hub, I can add users | 2 | Amina | Amr | Passant | 5 | 0.4
42 | As an Admin of the AWG Hub, I can delete users | 2 | Passant | Amr | Amina | 3 | 0.66667
Total velocity (sum of velocity)
31.85
Team velocity (Total velo / # of members)
2.8955
Speed Up Ratio
0.8631
Sprint 4
1.09
V4*I
0.94077