## Sheet1
Team name | Debugger | Guidelines | 1. Sort the user stories according to priority
Project | AWG |  | 2. Priority refers to how fundamental is the user story for the project ( For example : you cannot implement Sumerge without "add investor" user story )
Module | VGS |  | 3. For everyone: Registration and log-in will be implemented in later sprints (~ Sprint 3) - this is when we will cover this material in Labs
Scrum ID | 40-15533 |  | 4. Use the unique ID to structure the user stories. For example: If (1) is "Portfolio Development" module, then 1.1 and 1.2 … are the related user stories
Scrum Email | maha_mekdad@outlook.com / maha.mekdad@student.guc.edu.eg |  | 5. Only features to be implemented in later sprints can be left as epics.
Uniuqe ID | User story | Epic ? | Priority | Assignee
1 | As not logged/logged in user,
1.1 | I can go from the Hub Page to any of its subdomains (Clubs) for viewing/surffing them. |  | High | Sherry
1.2 | I can see on the AWG Hub's homepage the provided brief description of the clubs. |  | Medium | Sara
1.3 | I can view the public announcements made by AWGs' subdomains on the hub. |  | Medium | Amr
1.4 | I can view all the Events pages and see the description of the events. |  | Medium | Merna
1.5 | I can register on the AWG Hub (once) for viewing all the subdomains/clubs. |  | High | Maha
1.6 | I should be able sign in. |  | High | Maha
1.7 | I can view other users profiles. |  | Medium | Sara
1.8 | I can view FAQs on the hub |  | Medium | Sara
1.9 | I can contact with the club through a contact us page, that sends the content directly to the club’s email. |  | Medium | Osama
1.1o | I can check out the about us page that contains all of the info about the VGS club. |  | Low | Seif
1.11 | I can attend public events by providing National ID number in the form |  | High | Merna
1.12 | I can search through the all Hub and get all of the results that are related to my search term like searching for the AWGs subdomains, events and others. |  | High | NO ONE
2 | As a logged in user,
2.1 | and not a member of the club, I should be able to click and fill in the application form. |  | High | Maha
2.2 | and not a member of the club, I should be able to click and edit the fields of my application form. |  | Medium | Maha
2.3 | I should be able to view (keep track of) my application to review the status. |  | Medium | Maha
2.4 | I should be able to fill public event forms to submit the fact that I am attending. |  | High | Merna
2.5 | I can upload a game on my profile and showcase it for try outs. |  | High | NO ONE
2.6 | I should be able to fill out private club event forms to be able to attend them. (in vgs club) |  | High | Merna
2.7 | I should be able to upload games on my profile so that people who visit the website can see them and act as a recommendation for them, or broaden their gaming horizon, and upload with it (screenshots, contributor users’ names, download link, and/or a video). |  | High | NO ONE
3 | As an Admin of AWG,
3.1 | I can edit the FAQs section. |  | Medium | Sara
3.2 | I can add users |  | High | Amina
3.3 | I can edit users |  | Medium | Amr
3.4 | I can delete users |  | Medium | Passant
4 | As a President,
4.1 | I should be able to raise a vote to replace myself, and If all the directors agree and they all accepted the same nominated person, I can be changed. |  | High | Maha
4.2 | I should be able to edit accounts of users or remove users under me. |  | Medium | Sherry | *
4.3 | I can easily access a page that contains all the information of my present and past applicants. |  | Medium | Seif | *
4.4 | I can view the attendances of all the club’s members/ heads/ directors. |  | Medium | Omar
5 | As a Director,
5.1 | I should be able to raise a vote to replace the president with one of the current advisors or directors if they fit, and (if all the other directors vote also for the same person) it’s a unanimous vote that all the advisors/directors agree on |  | High | Maha
5.2 | I should be able to edit accounts of users or remove users under me |  | Medium | Sherry | *
5.3 | I can easily access a page that contains all the information of my present and past applicants. |  | Medium | Seif | *
5.4 | I can view the attendance of the mentors or heads and members. |  | Medium | Omar
5.5 | I can view a specific request to check its data. |  | Medium | Merna
5.6 | I can edit status of a request to refuse or accept it. |  | Medium | Merna
6 | As a Head,
6.1 | I can send a request to my Director asking for a permission to edit the user profiles under my committee to remove unapproved content. |  | High | Merna
6.2 | I can view specific request to check for acceptance or rejection. |  | Medium | Merna
6.3 | I should be able to add members or remove them from my committee. |  | High | Sherry
6.4 | I can access a page that contains all the information related only to my committee's present and past applicants. |  | High | Seif
6.5 | I can view the attendance of the recruits or members in the same branch. |  | High | Omar
6.6 | I should be able to create/ view/ edit my own interview slot sheet which is a table that indicates my free slots. |  | High | Ghada
6.7 | I can view the application form of my committee for accepting, binding, or rejecting the applicant. |  | Medium | Maha
7 | As a Boothmember,
7.1 | I should be able to book/change interview times in respect to the free slots in the interview sheets of the heads. |  | High | Ghada
8 | As a HR Head,
8.1 | I can assign the booth members. |  | High | Ghada
9 | As a President/Director/Head,
9.1 | I should be able to edit the attendance sheets of the members. |  | Medium | Seif
9.2 | I should be able to add notes to the users under me (or in the same committee for Heads) to be reviewed later on |  | High | Sherry
9.3 | I can create a group to send announcements to whom I choose and it's only controlled and accessible by me |  | High | Ghada
9.4 | I can post announcements whether to a committee or a specific user, and I can post with it whether a text, pdf, or picture. |  | High | Omar
9.5 | I can view event submission forms to filter through them. |  | Medium | Osama
9.6 | I can view the application forms for accepting, binding, or rejecting the applicant. |  | Medium | Maha | *
9.7 | I can edit the amount, the start and end of the interview slots. |  | Medium | Amr
10 | As a “Member/Head/Director/President” I should be able to create/view my attendance. |  | High | Omar
11 | As a Marketing Head/Directors/President, I can add/edit/remove events. |  | Medium | Osama